## Summary
LMNS Equity and Equality Action Plan: Norfolk and Waveney LMNS
Add Logo
Executive Summary | Equity means that all groups in society can achieve health outcomes that are as good as those for the most socially advantaged group.2 Addressing inequities requires action on the social determinants of health as well as the health determinants. Therefore, the NHS cannot achieve equity in health outcomes alone – it needs support from the public, private and third sectors. The Marmot review called for action to be universal, but with a scale and intensity proportionate to the level of disadvantage; this is known as ‘proportionate universalism’. To do this maternity and neonatal services need to respond to each person’s unique health and social situation – with increasing support as health inequalities increase – so that care is safe and personal for all. This action plan reflects the five health inequalities priorities described in the 2021/22 priorities and operational planning guidance: Implementation guidance, and sets out how the Norfolk and Waveney LMNS aligns with the health inequalities work of the Intergrated Care System. The plan and all evidence for completed projects has been published online alongside a service user facing Padlet.
Online Publication
Padlet
Equity and equality: Guidance for local maternity systems (england.nhs.uk)
Action Plan Contents | 1. Vision, Values & Aims
2. Detailed Action Plan
3. Population
4. Co-Production
5. Roles & Responsibilities
6. Resources
7. Communication Plan
8. Measurement Plan
9. Sustainability

## Glossary of Terms
Term/ Acronym | Definition
BME | Black and Minority Ethnic
CAN | Community Action Norfolk
CCG | Clinical Commissioning Group
CNST | Clinical Negligence Scheme for Trusts
E&E | Equity and Equality
EDI | Equality Diversity and Inclusion
EIS | Early Implementer Schemes
Equality | To ensure that every individual has an equal opportunity to make the most of their lives and talents
Equity | The absence of avoidable or remediable differences among groups of people, whether those groups are defined socially, economically, demographically or geographically.
FNP | Family Nurse Practitioners
GDM | Gestational Diabetes Mellitus
GP's | General Practitioners
GRT | Gypsy and Roma - Travellers
HCP | Healthy Child Programme
HOM's | Heads of Midwifery
HR | Human Resources
ICB | Integrated Care Board
ICS | Integrated Care System
Inclusion Health Groups | Groups of people who have not usually been well provided for by healthcare services, and have poorer access, experiences and health outcomes. The definition covers people who are homeless and rough sleepers, vulnerable migrants (refugees and asylum seekers), sex workers, and those from Gypsy, Roma and Traveller communities
JoN | Just One Norfolk
JPUH | James Paget University Hospital
JSNA | Joint Strategic Needs Assessment
KPI's | Key Performance Indicators
LGBQT+ | Lesbian, Gay, Bi-sexual, Queer, Trans, Plus group
LMNS | Local Maternity and Neonatal System
MBRRACE | Mothers and Babies Reducing Risks through Audits and Confidential Enquiries
MCoC | Maternity Continuity of Carer
MHS | Maternal Health Assistants
MIS | Maternity Incentive Scheme
MMN | Maternal Medicine Networks
MOU | Memorandum of Understanding
MSDS | Maternity Services Data Set
MVP's | Maternity Voice Partnerships
N&W | Norfolk and Waveney
NCC | Norfolk County Council
NHS | National Health Service
NHS LTP | National Health Service Long Term Plan
NNUH | Norfolk and Norwich University Hospital
NRT | Nicotine Replacement Therapy
NSFT | Norfolk and Suffolk NHS Foundation Trust
OHID | Office of Health Improvement and Disparities
P2P | Pathway to Parenting
PAS | Patient Administration System
PCN's | Primary Care Networks
PCSP | Patient Care and Support Plans
PDM's | Practice Development Midwives
Perinatal Mental Health | Perinatal mental health problems are those which occur during pregnancy or in the first year following the birth of a child.
Perinatal Mortality | Stillbirths and early neonatal deaths.
PHE | Public Health England
PMH | Perinatal Mental Health
PMRT | Perinatal Mortality Review Tool
Protected characteristics | As set out in the Equality Act 2010, these are age, disability, gender reassignment, marriage and civil partnership, race, religion or belief, sex, sexual orientation and pregnancy and maternity.
PSIRF | Patient Safety Incident Response Framework
QEH | Queen Elisabeth Hospital, Kings Lynn
SATOD | Smoking at time of delivery
SI | Serious Incident
SOP | Standard Operating Practice
TAP's | Therapy Assistant Physiotherapists
VCSE | Voluntary , Community and Social Enterprise
WRES | Workforce Race Equality Standard

## Vision
Vision
Overall Vision | Our two aims relating to equity and equality for maternity and neonatal care are to improve: • equity for mothers and babies from Black, Asian and Mixed ethnic groups and those living in the most deprived areas • race equality for staff.
Values | Value | Rationale | Key Actions
| Proportionate universalism | To ‘raise and flatten’ the inequalities gradient, universal action is needed with a scale and intensity that reflects need. | This is the National Vision which as an LMNS we agree to and as we progress with the work we will review this to ensure it continues to meet the needs of the local population
| Collaboration | Achieving equity will require unity and co-ordinated effort across many stakeholders, especially to tackle the social determinants of health. | This is the National Vision which as an LMNS we agree to and as we progress with the work we will review this to ensure it continues to meet the needs of the local population
| Co-production | Interventions are more likely to be culturally and socially relevant and clinically effective if parents and staff work in partnership to improve clinical quality. | This is the National Vision which as an LMNS we agree to and as we progress with the work we will review this to ensure it continues to meet the needs of the local population
Aims | List the key aims of the equity strategy, which should align with any ICS aims relating to health inequalities
to become safer, more personalised, kinder, professional and more family friendly; where everywoman has access to information to enable her to make decisions about her care; and where she and her baby can access support that is centred around their individual needs and circumstances.
for all staff to be supported to deliver care which is women centred, working in high performing teams, in organisations which are well led and in cultures which promote innovation, continuous learning, and break down organisational and professional boundaries
Equity for the unique and diverse population of Norfolk and Waveney which includes Traveller communities, disabled, Special Educational Needs, Migrant Populations, Refugees, Homeless, Service Women, Trafficked women, Prisoners, Domestic Violence, Women in the Service Industry and Black, Asian and Minority Ethnic Groups
To align with the CORE20PLUS5 + Smoking and workstreams
To reflect the emerging ICS/ ICB aims and Health Equity Strategy as they evolve and develop following transition from the CCG
ICS Interdependencies | List any ICS interdependencies that those using this action plan should be aware of
PHE, OHID, NCC, PCN's Healthy Child Programme, Provider Trusts, Voluntary Sector, MVP's, Region

## Priority 1
Priority 1: Restore NHS Services Inclusivity | [11 empty] | RAG
Description |  |  |  |  | Process indicator |  |  |  | Outcome indicator
At national level, the decline in access among some groups during the first wave of the pandemic broadly recovered in later months. Some pre-existing disparities in access, experience and outcomes have widened during the pandemic. |  |  |  |  | Implementation of the COVID-19 four actions |  |  |  | Women and birthing people using folic acid |  |  | Not started | In progress | Due | Overdue | Closed
Intervention | Covid-19 four actions | No. | Action | Detail | Key Milestones | Person responisible | Workstream | Target date | RAG | Metrics for Success | Comments/Updates/Evidence | Q4 2022 |  |  | Q1 2023 |  | Q2 2023
Intervention 1: Continue to implement the covid 19 four actions | 1. Increase support for at-risk pregnant women and birthing people – for example, make sure clinicians have a lower threshold to review, admit and consider multidisciplinary escalation in women and birthing people from ethnic minority groups. | 1.1 | COVID-19 LMNS shared guidelines | Ensuring that all trusts have implemented and are using COVID-19 guidelines inline with national recommendations | Obtaining guidelines from all trusts and confirmation of implementation | Better Births Lead Midwife | Quality and safety | 2021-12-01 |  | Monitoring effectiveness of guideline by Audit of COVID BME paitents care | Alll trusts has guidelines inline with national reccomendations | https://improvinglivesnw.org.uk/our-work/healthier-communities/maternity-services/maternity-equity-and-equality-strategy/?limit=10&offset=0
|  | 1.2 | Vaccination hubs | To confirm the vaccination process with each trust, ensuring that at risk- women and birthing people are offered vaccinations | Confirmation via trust | Better Births Lead Midwife / guideline leads | Quality and safety | 2022-11-01 |  | Obtaining vaccination statistics from each trust | Vaccination hubs were set up during height of pandemic. Now closed as vaccination is offer as part of antenatal pathway
|  | 1.3 | LMNS buddy with Cambridgeshire and Peterborough | To collabroate on staff equity stratgey and PMRT external review | Publication of staff survey equity results | Lead Midwife/ Better Births Lead Midwife | National | 2022-07-01 |  | obtaining a clear oversight of equity amoung staff | Production of the Maternity Staff Ethnicity video completed and circulated
| 2. Reach out and reassure pregnant BME women and birthing people with tailored communications. | 2.1 | JON translation services | To promote resources and translations via JON to maternity staff | Collaboration with JON and trusts to promote services | JoN, Better Birth Lead Midwives, MVP's | Data and digital | 2021-02-01 |  | Translation service live on JON | https://www.justonenorfolk.nhs.uk/pregnancy-early-days/ | https://www.justonenorfolk.nhs.uk/pregnancy-early-days/
|  | 2.2 | Multilingual padlets | Update padlets to include multilingual resources | understanding the need for different languages and supported development of padlet information with MVP's | Better Births Lead Midwife | Data and digital | 2021-02-01 |  | Active Padlet | Norfolk and Waveney LMNS Multilingual maternity resources (padlet.com) | Norfolk and Waveney LMNS Multilingual maternity resources (padlet.com)
|  | 2.3 | Webinar | To develop and host information webinars for services users | Producing webniars with translation avaliable | Project Manager | Transformation | 2021-03-01 |  | Confirmation of translated webinars and statistic regarding engagement | Webinars completed for Covid, Breastfeeding and Pelvic health. Ongoing webinars planned. Further work required to understand how the webinars can be translated. Webinars launched from March 2021
|  | 2.5 | P2P parent education | Collaboration with the Health Child Programme | Established key stakeholders at P2P development working group | Lead Midwife/ Public Health Midwife | Prevention | 2023-01-01 |  | Provision of P2P education | Regular multidisaplinary working group meetings to refresh the P2P
| 3.Ensuring hospitals discuss vitamins, supplements and nutrition in pregnancy with all women and birthing people. | 3.1 | LMNS wide Vitamin D Guideline/ SOP | To ensure system-wide pathways for the promotion and provision of Vitamin D for pregnancy | Approved SOP and agreement from guideline committees | Better Births Lead Midwife / Obstetricians | Prevention | 2022-11-01 |  | Audit Vitamin D uptake once pathway is implemented | Vitamin D gudeline written and approved for NNUH and JPUH, awaiting approval at QEH
|  | 3.2 | Healhty start vouchers | To simplify the application process and improve accesibility for women and birthing people online | Online application process live | Head of Communities and Partnerships, Childrens Services | Prevention | 2021-04-01 |  | Online application process | Applying for Healthy Start – Get help to buy food and milk (Healthy Start) | Applying for Healthy Start – Get help to buy food and milk (Healthy Start)
|  | 3.3 | Vitamin D Baby TV (Baby and child) | Healthy Child Programme creating a video for Vitamin D during pregnancy | Collaboration with HCP and promotion of video. | Healthy Child Programme/ JoN | Prevention | 2021-12-01 |  | Video avaliable on JON | Vitamin D (justonenorfolk.nhs.uk) | Vitamin D (justonenorfolk.nhs.uk)
|  | 3.4 | Healthy eating project | To ensure the promotion of healthy eating during pregnancy, including foods rich in Vitamin D. | Collaboration with Local Authorities and community organisations to promote health eating and weight management during pregnancy | Public Health Midwife/ Advanced Public Health Officer for NCC | Prevention | 2022-12-01 |  | Currently paused, awaiting new OHID representation | Currently paused, awaiting new OHID representation
| 4. Ensure all providers record on maternity information systems the ethnicity of every woman and birthing person, as well as other risk factors, such as living in a deprived area (postcode), co-morbidities, BMI and aged 35 years or over, to identify those most at risk of poor outcomes. | 4.1 | MSDS data reporting | To ensure that all reporting is in line with national requirements and ensure robust reporting pathways | None | Digital Midwife | Data and digital | 2021-04-01 |  | All systems have the data with varying degrees of compliance. A couple of trusts, the PAS overrides the ethnicity and it appears that it has not be entered. Making sure that this can be addressed to avoid overide. | Completed
|  | 4.2 | Heat mapping survey | Conduct heat mapping survey in collaboration with MVP's | Use survey to inform key services within maternity | Head of Public Health Information, NCC/ OHID | Transformation | 2021-12-01 |  | Produce Heat Mapping Survey | Completed

## priority 2
Priority 2: Mitigate against digital exclusion | [10 empty] | RAG
Description |  |  |  | Process indicator |  |  |  | Outcome indicator
Systems are asked to ensure that: • providers offer face-to-face care to patients who cannot use remote services • more complete data collection is carried out, to identify who is accessing face-to-face, telephone or video consultations, broken down by relevant protected characteristic and health inclusion group • they take account of their assessment of the impact of digital consultation channels on patient access. |  |  |  | The number of women and birthing people with a Personalised Care and Support Plan which covers: o antennal care by 17 weeks' gestation o intrapartum care by 35 weeks' gestation o postnatal care by 37 weeks' gestation The numbers of women and birthing people who had all three of the above in place by the gestational dates All indicators are available with breakdowns by ethnicity and index of multiple deprivation (source: MSDS) |  |  |  | None |  |  | Not started | In progress | Due | Overdue | Closed
Intervention | Detail | No. | Action | Key Milestones/ description | Person responisible | Workstream | Target Date | RAG | Metrics for Success | Comments/Updates | Q4 2022 |  |  | Q1 2023 |  | Q2 2023
Ensure personalised care and support plans (PCSPs) are available in a range of languages and formats, including hard copy PCSPs for those experiencing digital exclusion | Personalised care and support plans (PCSPs): The NHS Long Term Plan asks integrated care systems (ICS) to implement PCSPs in maternity services. This tool supports and documents the conversations and decision-making process from which an agreed plan is developed that reflects an holistic assessment of the woman’s health and wellbeing needs. The PCSP should set out a woman’s decisions about the care and support she wants. Women and birthing people need evidenced-based information in advance of decision-making so that they are well prepared. | 1.1 | Digital PCSP's in all trusts | To collaborted with MVP's to undertake a survey of service users requirements | Digital Midwives/ MVP's | Digital/ Transformation | 2022-03-23 |  | As per process indicator above | Desgining PCSP's is in progress, and a survey is planned for understanding service user needs on postnatal wards . Digital PCSP are in place at QEH, and paper PCSPs at N& N & JPH. . Both N& N and JPH are working towards a digital PCSP which had early collaboration with the MVPs. The product will be available to users by end of 2022/23. Once in place the aim is for user feedback to the supplier to enable further co-production
|  | 1.2 | Digital bid | Application for bid submitted | Digital Midwife | Digital | 2022-04-01 |  | Successful bid
|  | 1.3 | Library project to reduce digital poverty in pregnancy | To collaborate with Norfolk Libraries to offer a digital gifting scheme | Lead Midwife/ Public Health Midwife | Prevention | 2022-01-22 |  | Uptake of digital gifting | Digital gifting scheme launched. Poor uptake at present.
|  | 1.4 | Dasboards | Process indicators for this element should be included in monthly dashboard data. | Digital Midwife | digital and data | 2023-03-01 |  | Monthly Dashboard Data
|  | 1.5 | Deprivation monies project | To collaborate with third sectior organisation to bid for funding from the deprivation monies. Development of application process and applications received | Lead Midwife/ HOM's | Transformation | 2022-06-01 |  | Number of successful applications and co-produced plans for enhance support for the pregnant population

## Priority 3
Priority 3: Ensure datasets are comeplete and timely | [10 empty] | RAG
Description |  |  |  | Process indicator |  |  |  | Outcome indicator
Systems are asked to continue to improve the collection and recording of ethnicity data. NHS England and NHS Improvement will support the improvement of data collection, including through the development of the health inequalities improvement dashboard. |  |  |  | Safety action 2, category 9: data submitted to Maternity Services Data Set (MSDS) contains valid postcode for mother at booking in 95% of women booked in the month. • Ethnicity data quality (source: Regional Measures Report). • Safety action 2, category 10: data submitted to MSDS includes a valid ethnic category for at least 80% of the women and birthing people booked in the month. Not stated, missing and not known are not valid records. |  |  |  | None |  |  | Not started | In progress | Due | Overdue | Closed
Intervention | Detail | No. | Action | Key Milestones | Person responisible | Workstream | Target Date | RAG | Metrics for Success | Comments/Updates | Q4 2022 |  |  | Q1 2023 |  | Q2 2023
Intervention 1: On maternity information systems continuously improve the data quality of ethnic coding and the mothers postcode. | Data quality: recording ethnicity and postcode data at booking helps clinicians and LMNS understand how health outcomes vary by geographical area and ethnicity. Services can then identify and prioritise those groups with poorer health outcomes for whom service improvements are needed. NHS Resolution’s Maternity Incentive Scheme supports the delivery of safer care by giving trusts a significant financial incentive to achieve 10 safety actions. Safety action 2 supports data quality improvement. | 1.1 | Safety action 2 category 9: Data submitted to MSDS contains valid postcode for mother at booking |  | Digital Midwife | Quality and Safety | Aug 22 |  | April 22 Data National Dashboard AOD data collected : JPH 99% / NNUH 100% / QEH 100% | Maternity information systems collate Postcodes that are then linked to the AOD table
|  | 1.2 | Safety action 2, category 10: data submitted to MSDS includes a valid ethnic category |  | Digital Midwife | Quality and safety | 2022-11-22 |  | April 2022 MSDS : JPH 77.1 % (135/175) / NNUH 96.7% (440/455) / QEH 96.7% (145/150) | JPH are investigating prcocess to improve data quality
|  | 1.3 | To ensure that the dashboards are a regular agenda item on MVP meetings | Dashboards shared at MVP meetings | MVP/ Digital Midwife | Digital and data | 2022-02-23 |  | 1 co-produced MVP dasboard across the 3 trusts - MVP engagement required | NNUH and QEH have differring co - produced MVP dashboards. JPH requires investigating.
|  | 1.4 | Reporting to LMNS board | Process indicators to be included on monthly dashboard data. | Digital Midwife | Digital and data | Dec 22 |  | external company funded tto undertake Dashboard production
|  | 1.5 | Ensure Badgernet and maternity system align to support accurate neonatal reporing |  | Neonatal team/ PDM's | Digital and data | 2023-12-01 |  | Aligned systems | LMNS has undertaken a deep dive and demonstarted that there is variation between maternity and Neonnatal data. and highlighted that teh ODN daat only reflects activivity for babies admitted to NICU. Digital MWs at each trust are guided to undertake weekly/ monthly review of babies meeting the criteria and verify data between maternity and neonatal services
|  | 1.7 | Neonatal Critial Care Review |  | Emma Wiskin/ Lydia Gerrie | Neonatal

## Priority 4a
Priority 4a: Accelerate preventative programmes that engage those at greatest risk of poor health outcomes, Understand your population and co-produce interventions | [11 empty] | RAG
Description |  |  |  |  | Process indicator |  |  |  |  | Outcome indicator
• Understand the local population – its health outcomes and community assets. • Understand staff experience, using Workforce Race Equality Scheme data. • Use this understanding to plan co-production activity to design interventions to improve equity for women, birthing peopleand babies and race equality for staff. |  |  |  |  | None |  |  |  |  | None |  | Not started | In progress | Due | Overdue | Closed
Intervention | Detail | No. | Action | Description | Key Milestones | Person responisible | Workstream | Target Date | RAG | Metrics for Success | Comments | Q4 2022 |  |  | Q1 2023 |  | Q2 2023
1. Understand the local populations maternal and perinatal health needs | It is time to review and refresh the population needs analysis for maternity services. The refresh should include an analysis by ethnic group (particularly Black, Asian and Mixed ethnic groups) and those living in the most deprived areas. LMS should consider other protected characteristics and inclusion groups where local data and/or intelligence indicates health inequalities are present. | 1.1 | Local data and heat mapping | To undertake an equity and equality needs assessment with OHID | Publishable document | Head of Public Health Information, NCC/ Better Births Lead Midwife / Public Health Midwife | Tranformation/ prevention | 2022-07-01 |  | Publishable document | Initial equity and equality needs assessment completed, however, a lack of readily avaliable data and digital immaturity in maternity services has results in a basis understanding. Further data collection and analysis is required to understand our pregnant population
|  | 1.2 | Phase 2 data collection and analysis | To gain a deeper understanding our population health needs and social determinants of health | Publishable document | Digital Midwife/ Public Health Midwife | Tranformation/ prevention | 2021-12-01 |  | Publishable document | Further metrics discussion with Delyse
|  | 1.3 | Pelvic Health project | Norfolk and Waveney are EIS's for pelvic health project. Developing a single point of access and to capture data for pelvic health dysfunction in relation to ethincity/ deprivation | 3 X TAP's employed | Project Manager/ Pelvic Health Physiotherapist | Prevention | 2024-01-01 |  | Metrics as per Pelvic Health Project | Good progress with the Pelvic health project. 3X TAP's in post. E-PAQ now live and Squeezy app avaliable for free.
|  | 1.4 | Smoking in pregnancy project | New Tobacco dependance treament service for pregnant women, in line with the NHS LTP | Launch of new service at JPUH | Public Health Midwife | Prevention | 2024-01-01 |  | Data capture ethnicity/ deprivation/ smoking in pregnancy | Due to Launch at JPUH in October 2022
|  | 1.5 | Alcohol in pregnancy project | To provide accurate information regarding alcohol consumption during pregnancy | Established multidisaplinary working group | Public Health Midwife/ Advanced Public Health Officer for NCC | Prevention | 2023-01-01 |  | Engagement with JON Alcohol in pregnancy page and collection of agreed metrics | New alcohol in pregnancy information page launched on JON
|  | 1.6 | LGBQT+ and inclusive language work | To agree inclusive language for maternity services | Collaboration with LGBQT+ Norwich Project | Public Health Midwife / LGBQT project norwich | Prevention | 2022-11-01 |  | Publishable documents | Contact made with LGBQT+ Norwich Project, outlined required work but need to identify funding
|  | 1.7 | City of Sanctuary | Present idea to each traust to adopt each Maternity unit as Maternity Units of sanctuary | sucessful complation of the Learn, Embed and Share Phases of the award. | Better Births Lead Midwife/ City of Sanctuary | Transformation | 2024-08-01 |  | Eash trust sucessful award of Sanctuary status | Contact made with City of Sanctuary Norwich
2: Map the community assets. | Health assets are factors or resources that enhance health and wellbeing. They can be ‘social capital’ (networks, friendships, faith-based groups); public, private and third sector resources that support communities; physical and economic resources (such as buildings and employment); or the skills, knowledge and capacity of residents. | 2.1 | Comminty asset mapping | To understand and map the community assets for women, pregnant people and families in Norfolk and Waveney | Publishable document | Head of Public Health Information, NCC/ Better Births Lead Midwife / Public Health Midwife / Advanced Public Health Officer NIHR | Transformation/ prevention | 2021-11-01 |  | Publishable document | Initial asset mapping included in the equity and equality needs assessment. | See Equity and Equality Needs Assessment
|  | 2.3 | Healthwatch project | Collaborate with healthwatch to understanding valuable community assets | Designing and undertaking survey | Public Health Midwife/ Lead Midwife / Healthwatch | Prevention | 2023-01-01 |  | Completed survey | Initial contact made- need to confirm cost and funding
3: Experience of maternity and neonatal staff by ethnicity using WRES | human resources departments can provide WRES data for maternity and neonatal services. The data can be used to identify priorities for action and inform staff engagement processes which aim to improve the experience of staff from ethnic minority groups. | 3.1 | Collection of WRES data | To understand improvements in the workforce with respect to Black & Minority Ethnic staff | Presented in public document | Better Births Lead Midwife/ Public Health Midwife / Trust HR | Transformation | 2021-11-01 |  | Published WRES data | WRES data capture for Norfolk and Waveney as a whole to protect aminimity of BAME staff
|  | 3.2 | Collaboration with ICS EDI leads | Core20Plus5 work to be implemented by ICS, is there are health inequalities workstream? | Identify leads and establish contact | Public Health Midwife | Prevention | 2022-09-01 |  | Networking | Alice Vickers- Intergration and partnerships manager ICS. Contact made and will have oversight of this strategy
|  | 3.3 | Overseas recruitment | Look at international recruitment process across the LMNS | LMNS wide internation recruitment strategy and training package | Lead Midwife / HOM's | Workforce | 2024-08-01 |  | Recruitment
4. Set out a plan to co- produce interventions to improve equity | The co-production plan will outline the activity to co-produce interventions to improve equity for mothers, babies and race equality for staff. It can be a simple list of dates, meetings, groups to be consulted and the time allocated for the consultation discussion. This allows flexibility in where co-production takes place: at dedicated meetings, through existing meetings and/or outreach activities. The groups consulted should reflect those experiencing the greatest health inequalities, as described in the population health needs assessment | 4.1 | Co-production plan | See co-production tab | [5 empty] | See co-production tab | See co-production tab

## Priority 4b
Priority 4b: Accelerate preventative programmes that engage those at greatest risk of poor health outcomesAction on maternal mortality, morbidity and experience | [10 empty] | RAG
Description |  |  |  | Process indicator |  |  |  | outcome indicator
LMNS are asked to ensure equity in access, experience and health outcomes for women from Black, Asian and Mixed ethnic groups and those women living in the most deprived areas. They may consider other protected characteristics and inclusion groups. |  |  |  | The Maternal Medicine Network is implementing the KPIs in the nonmandatory national service specification. They are broken down by level of deprivation of the mother’s postcode and ethnicity • Booking at <70 days gestation (source: Regional Measures Report) • Proportion of women with complex social factors who attend booking by 10 weeks, 12+6 weeks and 20 weeks (source: Regional Measures Report) • For each complex social factor grouping, the number of women who: attend for booking by 10, 12+6 and 20 weeks; and attend the recommended number of antenatal appointments • % of parent members of the MVP who are from ethnic minority groups • % of women attending the booking appointment who are from ethnic minority groups (source: Regional Measures Report) • Ethnicity data quality (source: Regional Measures Report) |  |  |  | None |  |  | Not started | In progress | Due | Overdue | Closed
Intervention | Detail | No. | Action | Key Milestones | Person responisible | Workstream | Target Date | RAG | Metrics for Success | Comments/Updates | Q4 2022 |  |  | Q1 2023 |  | Q2 2023
1. implement maternal medicine networks to help achieve equity. | Under the NHS Long Term Plan, maternal medicine networks will be established so that by March 2024 every woman in England with medical problems has access to specialist advice and care. The model service specification includes key performance indicators (KPIs) relating to outcomes and equalities and requires that information and guidance is co-produced, culturally competent and delivered through accessible channels. | 1.1 | Maternal Medicine Network | Maternal medicine launched at NNUH | Divisional Midwifery Director NNUH/ Lead Midwife | Transformation | 2022-03-01 |  | The Maternal Medicine Network is implementing the KPIs in the nonmandatory national service specification. They are broken down by level of deprivation of the mother’s postcode and ethnicity | Completed
|  | 1.2 | Collaboration with Maternal Medicine Network consultant body | Group organised and regularly meeting | Lead Midwife/ Programme Manager/ MMN Team | Transformation | 2022-03-01 |  |  | Completed
|  | 1.3 | Simulation training | Successful funding bid for £40,000 | PDM's/ MMN team | workforce | 2023-01-01 |  |  | Curriculum in development
2: Offer referral to the NHS Diabetes prevention programme | Where a woman or birthing person is diagnosed with GDM, maternity services should inform their GP practice. Women or birthing people with a history of GDM should be reviewed and offered testing for diabetes postnatally and subsequent annual checks (with a glycaemic test) by their GP practice as described in the NICE guideline [NG3] diabetes in pregnancy. | 2.1 | Prevention programme | All GP receive email notification from Trusts of identified patients. | Lead Midwife/ Public Health Midwife | Prevention | 2022-07-01 |  | Letters sent to GPs as required. Process review to check the system with GP surgery. (August 2022)
3: Implement NICE CG110 antenatal care for pregnant women and birthing people with complex social factors | MBRRACE-UK identified a group of women at severe and multiple disadvantage. The main elements of multiple disadvantage are a mental health diagnosis (women or birthing people with serious mental illness have a higher risk of obstetric near misses at the time of birth, emphasising the importance of integrated physical and mental healthcare before and during pregnancy for this group16), substance misuse and domestic abuse. | 3.1 | Review current provision/ scope at each trust | System-wide booking and assessments and system-wide PMMH guideline and fast follower for MMHS. | Better Births Lead Midwife | PNMH | 2021-06-01 |  | PNMH project system-wide.
|  | 3.2 | Capture process indicators | Confirmation and dashboard avaliable and NSFT have own dashboards too | Digital Midwife | PNMH | 2022-06-01
|  | 3.3 | Implement guideline at all 3 trusts | Referral pathways and SOPS in place at all Trusts. | Better Births leads/ Trust safeguarding teams | Q&S | 2022-11-01
4: Implement Maternal Mental health services with a focus of access by ethnicity and deprivation | When implementing maternal mental health services, LMS should consider the access to them by ethnicity and the level of deprivation of the mother’s postcode, in partnership with the local perinatal mental health (PMH) team. The PMH dashboard provides access data by ethnicity and deprivation | 4.1 | PMH Bid | Successfully won bid | Better Births Lead Midwife | PNMH | 2021-02-01
|  | 4.2 | Input into PMH workstream | NSFT collect data on referrals and service users accepting the service. | Better Births Lead Midwife | PNMH | 2022-08-01
|  | 4.3 | Lotus Team | Specialist Team set up | Better Births Lead Midwife | PNMH | 2022-04-01
5: ensure personalised care and support plans are available to everyone. | The NHS Long Term Plan asks ICS to implement PCSPs in maternity services. Personalised care and support planning guidance: Guidance for local maternity systems describes how to implement PCSPs, including the need for a risk assessment at every contact | 5.1 | See priority 2 for details | As per priority 2 | Digital Midwife/ MVP | Digital | 2023-03-01 |  | As per priority 2
6. ensure the MVPs in your LMS reflect the ethnic diversity of the local population, in line with NICE QS167. | NICE QS167 asks that those from ethnic minority groups “…are represented in peer and lay roles within local health and wellbeing programmes ….[to] encourage uptake of services among groups that may otherwise be reluctant to get involved” and help design interventions that are relevant to the local population | 6 | Mertic-% of parent members of the MVP who are from ethnic minority groups |  | Lead Midwife/ MVPs |  | 2022-12-01
|  | 6.1 | Collaboration with MVP and Community groups/voices including FNP to ensure representation. Travelling community invited to have a voice through contacts with Specalist liason Nurse. County-wide. | Increase in representaiton in the MVP from other diverse groups. | Lead Midwife | Prevention | Novemeber 2022
|  | 6.2 | MVP co-production plan completed and to be shared with the MVP | Plan to be discussed and developed with the MVP | Lead Midwife/ LMNS Programme Manager | workforce | 2022-10-01
|  | 6.3 | MVP Chairs working with BME reps collaboration with staff groups and community groups to make in roads into communities | Increase in BME among MVP . | Lead Midwife/ LMNS Programme Manager | workforce | 2022-10-01

## Priority 4c
Priority 4c: Action on perinatal mortality and morbidity | [10 empty] | RAG
Description |  |  |  | Process indicator |  |  |  | Outcome indicator
LMS are asked to address the leading causes of perinatal mortality and morbidity for babies from Black, Asian and Mixed ethnic groups and born to women living in the most deprived areas. LMS may consider other protected characteristics and inclusion groups. |  |  |  | Process indicators Outcome indicators • Placement on a continuity of carer pathway – Black/Asian women • Placement on a continuity of carer pathway – women living in the most deprived areas • Baby Friendly accreditation |  |  |  | Breast milk at first feed • Low birth weight (<2,500g for term births) • Deliveries under 27 weeks • Deliveries under 37 weeks |  |  | Not started | In progress | Due | Overdue | Closed
Intervention | Detail | No. | Action | Key milestones | Person responsible | Workstream | Target date | RAG | Metric for success | Comments/ updates | Q4 2022 |  |  | Q1 2023 |  | Q2 2023
Intervention 1: Implement targeted and enhanced continuity of carer | Under the NHS Long Term Plan, continuity of carer is being rolled out to most women. In accordance with the principle of proportionate universalism, by 2024 75% of women from Black, Asian and Mixed ethnic groups and a similar percentage of women from the most deprived areas will receive continuity of carer. | 1.1 | JPUH CoC implementation | Roll out MCoC by March 2024 as default method of care delivery | Better Birth Lead Midwife JPUH | Transformation | 2024-03-01 |  | Placement on a continuity of carer pathway – Black/Asian women • Placement on a continuity of carer pathway – women living in the most deprived areas | JPUH at 84% with plans to roll out final team Nov 2022.
|  | 1.2 | QEH CoC implementation |  | Better Birth Lead Midwife QEH |  |  |  |  | Plans in place and CoC plans were submitted. On-going recruitment and HUBS in place. Action plans has been signed off June 2022
|  | 1.3 | NNUH CoC Implementation |  | Better Birth Lead Midwife NNUH/ CoC Project Manager |  |  |  |  | Plans submitted June 2022. Project manager in place to plan delivery of MCOC and Midwifery HUBS
Intervention 2: implement a smoke free pregnancy pathway | The NHS Patient Safety Strategy sets a national ambition to increase the proportion of smoke-free pregnancies to 94% or more by Q1 2023/24. The NHS Long Term Plan is introducing a smoke-free pregnancy pathway for expectant mums and their partners that includes focused sessions and treatments. | 2.1 | NHS Long Term Plan for treating tobacco dependance in pregnancy | Staged roll-out across the LMNS, starting at JPUH which has the highest prevalence of smoking in pregnancy and deprivation | Public Health Midwife | Prevention | 2024-03-01 |  | 100% of pregnant smokers are offer intensive smoking cessation support by in-house specialist by March 2024 | Service due to launch 09/2022 at JPUH
Intervention 3: Implement an LMNS Breastfeeding strategy | Every LMS should agree and implement a breastfeeding strategy to ensure that women have the information and support they need, when they need it in maternity services and in the community. The strategy should include an analysis of feeding trends across the LMS, identifying variation and inequalities between communities, along with actions to address them with a focus on the most deprived areas. | 3.1 | Implement a system-wide breastfeeding strategy that has been co-produced | The LMNS breastfeeding strategy has been co-produced with the MVP's, infant feeding leads at each trust, the Healthy Child Programme and PHE | Lead Midwife/ Public Health Midwife | Prevention | 2022-07-01 |  | BFI accreditation for all 3 trusts | Aug-2022 Breastfeeding strategy launched across the LMNS by the Maternity Health Supporters during a bespoke online breastfeeding study day
Intervention 4: Culturally-sensitive genetics services for consanguineous couples | .Among unrelated couples, 2–3% of all births have a congenital abnormality, for first cousin couples this is around 6%.27 In some populations the higher risk of recessive genetic disorders accounts for some of the increased rate of congenital abnormality, infant and child mortality and serious illness. | 4.1 | Improving understanding about genetic inheritance among families and healthcare professionals and improving access to culturally-sensitive genetics counselling | All couples idenified at risk to be referred to MMN and increase pre-natal screening with GPs | Lead Midwife/ Public Health Midwife/ | Transfomration | 2023-07-01 |  | MMN and GP to confrm plans for pre-conception cre and referral to fetal medicine as required. | August GP liason meeting to dicuss plans . MMN contacted 08/08/22 to confirm process. Discussed with Dr Flindall wh will mak contact for LMNS to have invitation to multifaith groups to dicsuss their needs as a community.

## Priority 4d
Priority 4d: Support for maternity and neonatal staff | [10 empty] | RAG
Description |  |  |  | Process indicator |  |  |  |  | Outcome indicator
LMS are asked to: • equip maternity and neonatal staff to provide culturally competent care • ensure maternity and neonatal staff experience race equality in the workplace |  |  |  | • % of maternity and neonatal staff who attended training about cultural competence in the last two years • % of maternity and neonatal Serious Incidents relating to patient care with a valid ethnic code • % of Perinatal Mortality Review Tool cases with a valid ethnic code |  |  |  |  | • WRES indicators 1 to 8 for midwives and nurses in maternity and neonatal services |  | Not started | In progress | Due | Overdue | Closed
Intervention | Detail | No. | Action | Key Milestones | Person responisible | Workstream | Target Date | RAG | Metrics for Success | Comments/Updates | Q4 2022 |  |  | Q1 2023 |  | Q2 2023
Intervention 1: roll out multidisciplinary training about cultural competence in maternity and neonatal services. | The Nursing and Midwifery Council’s standards of proficiency for midwives include that midwives “demonstrate an understanding of and the ability to challenge discriminatory behaviour to promote equity and inclusion for all” and consistently provide and promote non-discriminatory care. | 1 | Bespoke training on N&W population of Eastern European service users delivered by NCC | 2021-07-01 | Lead Midwife | workforce | 2021-07-01 |  | 50 staff attended training
|  | 2 | Regular monitoring of training for Safeguarding and PREVENT which includes cultural compatency in all 3 Provider Trusts. | 2022-07-01 | Lead Midwife/ Better Births Lead Midwife | S&Q | 2022-07-01 |  | On-going monitring of mandatory education with Trust trajectories in place
|  | 3 | City of Sanctuary Training | Establish all three trusts as Maternity Units of Sanctuary | Better Births Lead Midwife | Transformation | Set 24 |  | Implement all three stages of sanctuary development | ESR training
Intervention 2: when investigating serious incidents, consider the impact of culture, ethnicity and language | Maternity services should ensure that: • the impact of parents’ culture, ethnicity and language is discussed and considered during the antenatal risk assessment process, initial assessment and follow-up • ethnicity is recorded for all serious incidents and PMRT cases • investigations consider whether the impact of culture, ethnicity and language on the woman’s needs was discussed and considered during the antenatal risk assessment process, initial assessment and follow-up. | 2.1 | SI surveillance meetings in Feburary 2022 | 2022-02-01 | Lead Midwife | Quality and safety | 2022-02-01 |  | Attendance and system-wide representation
|  | 2.2 | Ethnicity grouping on all datix and incident reports. When PSIRF is introduced, it includes ethnicity reports. | By January Trusts will have explored adding ethnic data to DATIX system and PSIRF wlill look to include this as it is introduced. | Lead Midwife / HOMS/ Patient safety Midwives | Quality and safety | 2023-01-01 |  | Ethnic data will be included in all incidents. Continuous audits taking place by S&Q team now and will become mandatory.
|  | 2.3 | The Maternity Fellowship | appointment of clinical fellow | ICB | workforce | 2022-09-01 |  |  | The Maternity Fellowship will focus on equity of access to health and care with the aim of improved health outcomes for this cohort. The Fellow will work with the Norfolk & Waveney ICS partners, to ensure that there is continued awareness of inequity with maternity services and play a key role in developing and implementing improvement projects with aligns with the equity and equality agenda.
Intervention 3: implement the Workforce Race Equality Standard (WRES) in maternity and neonatal services. | Of the nine WRES indicators, 1 to 8 are relevant to maternity and neonatal services. Human resources departments can support services to access data for midwives and nurses working in maternity and neonatal services; it is more difficult to ascertain WRES data for other staff groups at service level. NHS WRES experts support the implementation of the WRES; they can help LMS improve their understanding of race inequalities, embed best practice, contribute to all areas of the wider health economy and drive system change. | 3.1 | Obtain WRES data from HR departments |  | Better Births Lead Midwife/ HR in Trusts | Workforce | 2021-12-01 |  |  | Difficult to break down the smaller trust WRES data into Maternity Staff within the smaller hospitals as this risks individuals being identified.
|  | 3.2 | Analyse WRES data to inform services and learning | Presented in E&E publishable document | Public Health Midwife | Workforce | 2022-06-01 |  | Added to Public E&E document.

## Priority 4e
Priority 4e: Enablers | [10 empty] | RAG
Description |  |  |  | Process indicator |  |  |  |  | Outcome indicator
LMS are asked to create the conditions to help achieve equity by: • considering the factors that will support high quality clinical care • working with system partners and the VCSE sector to address the social determinants of health. |  |  |  | None |  |  |  |  | None |  | Not started | In progress | Due | Overdue | Closed
Intervention | Detail | No. | Action | Key Milestones | Person responisible | Workstream | Target Date | RAG | Metrics for Success | Comments/Updates | Q4 2022 |  |  | Q1 2023 |  | Q2 2023
Intervention 1: establish community hubs in the areas with the greatest maternal and perinatal health needs. | Community hubs help centre care around the woman and her family. Better Births recommended that community hubs “should be established, where maternity services…are provided alongside other family-orientated health and social services provided by statutory and voluntary agencies...[and] work closely with their obstetric and neonatal unit(s)”. | 1.1 | Esatablish hubs for JPUH | Hubs in place and in use. | Project Manager / Better Births Lead Midwife | Transformation |  |  | Hubs all in place and in use
|  | 1.2 | Establish hubs for QEH | Hubs in place and in use | Project Manager / Better Births Lead Midwife / Community Matron | Transformation | 2022-04-01 |  | Hubs all in place and in use
|  | 1.3 | Establish hubs for NNUH | One Hub in place | Project Manager / Better Births Lead Midwife / Community Matron | Transformation | 2023-01-01 |  | project manager in place and Ops manager writing new bussiness case bi-weekly meetings to identify finanicla agreement and Hub procuurement
|  | 1.4 | Family Hubs development | Family hubs in development | Project Manager / LMNS Programme Manager | Transformation | 2024-01-01 |  | NCC have secured finance and LMNS working with NCC to progress.
Intervention 2: work with system partners and the VCSE sector to address the social determinants of health. | Social determinants of health: the Marmot review states: “The health of the population is not just a matter of how well the health service is funded and functions…Health is closely linked to the conditions in which people are born, grow, live, work and age and inequities in power, money and resources – the social determinants of health…ethnicity intersects with socioeconomic position to produce particularly poor outcomes for some ethnic minority groups”. | Collaboration with VCSE support groups for our priority groups | Idenify our 'plus' groups inline with Core20plus 5, and idenifty community groups to support | Support pathway implemented | Better Births Lead Midwife | Prevention | 2027-08-01 |  |  | Continue collaboration with groups to hold listening events throughtout the 5 year plan
|  | Identify and contact VCSE sectors in Norfolk and Waveney | Establishing network of VCSE sectors and multi faith groups. | Compose contact list | Better Births Lead Midwife | Prevention | 2022-08-01 |  |  | Contacts available on 'communication' list.

## Priority 5
Priority 5: Strengthen leadership and accountability | [7 empty] | RAG
Description
LMS set out their shared vision in a Local Maternity Transformation Plan in 2017 and should now supplement this with a co-produced equity and equality action plan. The 2021/22 priorities and operational planning guidance: Implementation guidance sets out a two-step process for this: • by 30 November 2021, LMS are asked to submit an equity and equality analysis (covering health outcomes, community assets and staff experience) and a coproduction plan as set out in sub-priority 4a, interventions 1 to 4 • by 30 September 2022, LMS are asked to co-produce equity and equality action plan | [7 empty] | Not started | In progress | Due | Overdue | Closed
Intervention | No. | Action | Person responisible | Workstream | Target Date | RAG | Comments/Updates
Priority 5: Strengthen leadership and accountability | 1.1 | vision, values and aims that align to ICS plans to tackle health inequalities | N&W LMNS | All | 2022-09-01 |  | See 'Vision' tab
| 1.2 | A clear description of the LMS population and health outcomes, with a focus on those from Black, Asian and Mixed ethnic groups and those living in the most deprived areas. LMS may use local data to identify health inequalities experienced by those with other protected characteristics and for inclusion groups | Better Births Lead Midwife/ Public Health Midwife | All | 2022-09-01 |  | Inital Health Needs Analysis complete, however, more in-depth data and analysis is required to identify health inequalities experienced by those with other protected characteristics and for inclusion groups. ICS is currenlty undertaking a local analysis inline with the Norfolk and Waveney ICS Clinical Stratgey
| 1.3 | strong evidence of co-production from the outset and how parents and staff will be involved in implementation | Better Births Lead Midwife/ Public Health Midwife | All | 2022-09-01 |  | MVP's has sighted the E&E action plan and the LMNS has produced an engagement timeline
| 1.4 | all relevant interventions in priorities 1 to 4 | N&W LMNS | All | 2022-09-01 |  | Completed see evidence for priorities 1-4
| 1.5 | Interventions which are most likely to reduce health inequalities (considering both the size of the population affected and extent of the health inequalities). The plan will include core interventions and, where relevant, those that apply to selected LMNS. LMNS may wish to include additional interventions given the characteristics of their population and their operating context | All | All | 2022-09-01 |  | See Priorities 1-5
| 1.6 | actions, milestones and metrics (reflecting the indicators in priorities 1, 3 and 4), with responsible owners, timescales and monitoring arrangements | All | All | 2022-09-01 |  | See Measurement Plan
| 1.7 | a clear mechanism for ensuring continuous clinical quality improvement | All | All | 2022-09-01 |  | To update all priority actions quaterly
| 1.8 | roles and responsibilities: including of the ICS and provider executive board-level leads for health inequalities, LMS senior responsible owner, board-level safety champions, MVP(s), etc. | N&W LMNS | All | 2022-09-01 |  | Contacts for VSCE sectors scoped by Lydia Gerrie
| 1.9 | interdependencies with other ICS workstreams, for example, estates, workforce | All | All | 2022-09-01 |  | See 'Vision' tab
| 2 | resourcing, including how the funding for this purpose will be applied | Lead Midwife/ LMNS Programme Manager/ LMNS Finance | All | 2022-09-01
| 2.1 | a high-level stakeholder communication plan | Better Births Lead Midwife/ ICB Comms team | All | 2022-09-01

## Population
Population
Population Needs Analaysis | National requirement of ICS: “Working alongside local authorities and other partners we will continue to develop our approach to population health management and prevention so that people can play a more proactive role in promoting good health. ICSs will drive the shift to population health, targeting interventions at those groups most at risk, supporting health prevention as well as treatment. ICSs will take a lead role in tackling health inequalities by building on the Core20PLUS5 approach introduced in 2021/22”​ “We will produce a plan that targets resources to deliver the national Core20Plus5 plan in Norfolk and Waveney. This includes reducing health gaps for people who live in the least well off neighbourhoods compared to people who live in the most well off neighbourhoods, and five key areas of care shown to have the greatest impact on Health Inequalities. These are maternity, severe mental illness, long term breathing illnesses, early cancer diagnosis and high blood pressure”. - Core20Plus5 HIOG workstream National requirements, local commitment, principles for a dedicated workstream and where we are currently
Overview of Local Data | List sources of data/evidence currently available to build a picture of local population equity
e.g. JSNA, Fingertips, MSDS, qualitative data from surveys and service user feedback
Key Targets Identified | Please see Easy Read Analysis Document

## Co-Production
Co-Production & Engagement
Use this power/impact metrix to consider how to get the best from your co-production and engagement activities:
| Low Impact |  | High Impact
High Power | Keep stakeholders satisfied and review analysis of their position regularly |  | Keep key stakeholder fully engaged through ful communication and consultations
Low Power | Monitor stakeholders who are not actively involved |  | Keep stakeholders informed through full communication
Consider existing relationships or projects involving co-production, and how these might link to your equity aims |  | Project |  | Relevance to equity aims |  |  | Contact/ who was involved in the co-production
|  | Pelvic health project |  | Support with producing new literature needed to promote equity aims |  |  | Project Manager/ Pelvis Health Physiotherapist
|  | NHS LTP Tobacco dependance treatment service |  | High area of deprivation with high SATOD rates |  |  | Public Health Midwife/ Smoke Free Norfolk/ Trusts
|  | Digital gifting project (maternity connect) |  | collaboration with MVP and Norfolk Libraries to support families in digital poverty to ensure equal access |  |  | Public Health Midwife/ Norfolk Libraries/ MVPS
|  | Maternity Health Supporters |  | work with highest risk service users to ensure interventions and support are ofered to the most in need. This includes the Ukrainina Refugees and other migrants. |  |  | Public Health Midwife
|  | Deprivation Money Project |  | This money is to support CoC in areas of higest deprivation |  |  | Lead Midwife
|  | co-producation plan and SOP developed |  | to ensure that all current and future projects are co-produced in a systetaic way with the MVP |  |  | LMNS PDMS/MVPS
|  | All patient information leaflets are co-produced |  | To ensure service user voice and understanding |  |  | LMNS Programme Manager/ MVP's/ Better Birth Lead Midwifes/ Pelvic Health Team/ JoN/ HCP
|  | Choice Booklet |  | Choices booklet give an overview of all services provided acr |  |  | Project Manager/ MVP's/ Better Birth Lead Midwifes/ Trust HOMS
|  | Webinars |  | Suite of webinars including pelvic health, infant feeding, and Covid which was translated into 4 main languages in N&W. |  |  | Lead Midwife/ HCP
|  | Pathway to Parenting education and suite of webinars, |  | Online offer with translation in 80 languages. Bespoke one to one offer for the most vulnerable families. |  |  | Lead Midwife/ HCP
|  | Education for staff and service users. |  | To ensure service user voice is heard |  |  | LMNS PDMS/ MVP's/ Trust PDMS
|  | Maternal Mental Health Services |  | Implement Maternal Mental health services with a focus of access by ethnicity and deprivation | 4: Implement Maternal Mental health services with a focus of access by ethnicity and deprivation | 4: Implement Maternal Mental health services with a focus of access by ethnicity and deprivation | Better Births Lead Midwife/ Lotus Team/ PMH Workstream
Planned Co-Production |  | Aligned action |  | Relevance to equity aims |  |  | Who | Resources/support needed | Next steps
|  | 1.3.3.4 Healthy eating project |  | To ensure the promotion of healthy eating during pregnancy, including foods rich in Vitamin D. |  |  | MVP | OHID support | Progress as per project plan
|  | 2.1.1.6 Deprivation Monies Project |  | To collaborate with third sectior organisation to bid for funding from the deprivation monies. |  |  | Lead Midwife ICB/ Third sector organisations | Ensure sustainability | Await feedback and evaluation of projects
|  | 3.1.1.3. MVP dashboards |  | To ensure that the dashboards are a regular agenda item on MVP meetings |  |  | MVP/ Digital Lead MW | IT infastructure | NNUH and QEH have differring co - produced MVP dashboards. JPH requires investigating.
|  | 4a.1.1.4 Smoking in pregnancy project |  | New Tobacco dependance treament service for pregnant women, in line with the NHS LTP |  |  | Public Health Midwife/ MVP/ Smoke free Norfolk | NHS LTP Funding | Launch at JPUH Oct 2022
|  | 4a.1.1.4.5 Alcohol in pregnancy project |  | To provide accurate information regarding alcohol consumption during pregnancy |  |  | Public Health Midwife/ JON/ | JON | Launch alcohol in pregnancy page on JoN
|  | 4a.1.1.4.6 LGBQT+ Language and inclusion project |  | To agree inclusive language for maternity services |  |  | LGBQT+ Norwich Project/ Public Health Midwife/ MVP | LGBQT+ Charity | Progress with plan for listening and engagement events
|  | 4a.2.2.3 Healthwatch plan |  | Collaborate with healthwatch to understanding valuable community assets |  |  | Lead Midwife ICB/ Public Health Midwife/ Healthwatch | Funding | establish costs and funding
|  | 4a.3.3.3 International Recruitment |  | LMNS wide internation recruitment strategy and training package |  |  | ICB workforce Midwife | Funding | Appointment of ICB workforce Midwife
|  | 4a:4.4.1 Co-Production Plan |  | Establishing Co-Production |  |  | Tranformation Lead Midwife/ Public Health Midwife/ Project Manager | VCSE's collaboraion, venue hire and refreshments | Work to co-production event timeline

## Co-Production Event Timeline
| N&W Maternity Services Co-Production Event Timeline | November | December | January | February | March | April | May | June | July | August | September | October
Year 1 | Disabilities | [12 empty] | These Co-Production Events will be held online and invitations sent out to mailing lists of over 2800 VCSE Orgnaisations within N&W and members of their communities encouraged to attend
Refugees/Asylum Seekers/Homeless
BME
GRT & Military Families
LGBQT+
PNMH/Isolation
Year 2 | Disabilities | [12 empty] | Each Event will be themed according to the protected charicteristic to be discussed that session. All guests will be invited to discuss a statement or question which will be posed to the group
Refugees/Asylum Seekers/Homeless
BME
GRT & Military Families
LGBQT+
PNMH/Isolation
Year 3 | Disabilities | [12 empty] | Individuals can speak openly within the group or use the chat facility to enter comments
Refugees/Asylum Seekers/Homeless
BME
GRT & Military Families
LGBQT+
| PNMH/Isolation | [12 empty] | Following the event, a transcript will be recorded and a thematic analysis performed from the conversation.
Year 4 | Disabilities
Refugees/Asylum Seekers/Homeless
BME
GRT & Military Families
| LGBQT+ | [12 empty] | The transcrips and themes will be shared with the mailing list to confirm and this will be shared with the Trusts and used to help shape maternity servcies around what is needed and required by service users and VCSE Orgnaisations
PNMH/Isolation
Year 5 | Disabilities
Refugees/Asylum Seekers/Homeless
BME
| GRT & Military Families | [12 empty] | The Events will be held every month and the themes repeated 6 monthly over the 5 year period of this action plan. This will allow themes to emerge and be improved upon and relationships to form.
LGBQT+
PNMH/Isolation

## Roles & Responsibilities
Roles & Responsibilities VCSE's and Partners
Group | Organisation/Role
CAN | CEO Community Action Norfolk
Chair MVP and CAN
N&W ICS | Integration and Partnerships Manager
Lead Midwife IESCCG
Associate Director of Primary Care
Senior Programmes Advisor Noroflk Community Foundation
Refugees/Asylum Seekers | New Routes
Chief Executive New routes
Maternity Action
Asylum Seeker Nurse - Peoples from aborad team
Peoples from abroad team NCC
Charity Director English Plus
Chat and Playgroup leader English Plus
Project Coordinator British Red Cross Refugee Services - Norwich
Gyros
City of Santurary National Lead
Access
BME | Bridge Plus
Housing | Pathways Project Coordinator Shelter Norfolk
Gypsy/Roma/Traveller | Travelling community nurse
Specialist practitioner for Gypsy, Roma, Traveller and Migrant families Norfolk
One Voice
Services Manager Homestart Norfolk
Families/ community | Homestart Norfolk
Homestart in Suffolk
Family Action
Families together Suffolk
Prisoners/Offenders | Ormiston Families
Special Educational Needs and Disabilities/ Autism | Nansa
ASSD Autism
Young people | Map
YMCA
Isolation | Get me out the four walls
Parents First
resource and learning center/ jobs | Merchants place
Pregnancy loss | Time Norfolk
Domestic Abuse | Daisy programme & rowan project
Pandora Project
Sue Lambert Trust
Leeway Norfolk and Suffolk
Lighthouse Ipswich
PHOEBE Ipswich
Debt and Disability | DIAL Great Yarmouth
DIAL Lowestoft
DAB Ipswich
CAB Thetford

## Resources
Resources
Total Funding Allocated | Total amount allocated from Maternity Transformation, and any other relevant funding sources.
Detailed Budget | Item Description | Unit Price (£) | Quantity | Total (£) | Details/Comments | Actual Expenditure (£)
| MVP | £ 18 000 |  | 18000
| Training (including contraception training) |  |  |  | Unable to allocate monies as funding will depend on allocation of monies over the 5 year action plan.
| choices booklet |  |  |  | Unable to allocate monies as funding will depend on allocation of monies over the 5 year action plan.
| payment to HCP for JON |  |  |  | Need more info please Unable to allocate monies as funding will depend on allocation of monies over the 5 year action plan.
| Pelvic health |  |  | 211000 | Full cost of service including TAPs, Physio Practice Educator and Admin
| MMH costs |  |  | 180000 | Assume this is Mental Health Midwives?
| MMN costs |  |  | 97000 | This is N&W contribution to the total cost of the 2 regional MMN's (the full cost of the MMN at NNUH is £350k)
| MHA posts (pre-birth clininc) |  |  | 97000 | Health Promotion MSWs
| Digital gifting |  |  | 8000
| Outreach work with voluntary sector |  |  | 70000
| Project manager will support MVP |  |  | 53000
| on-going innovative education with translation costs |  |  |  | Unable to allocate monies as funding will depend on allocation of monies over the 5 year action plan.
| development of LMNS website |  |  |  | Unable to allocate monies as funding will depend on allocation of monies over the 5 year action plan.
| smoking advisors and NRT |  |  | 146000 | Full cost of service is currently unknown, Team at JPH now in post - risks around total NRT cost
|  |  | Total/Actual Cost (£) | 880000 |  | 0

## Communication Plan
Communications Plan
Subject | Key Messages | Audience | Format/Platform? | Target Date(s) | Comments
What subject do the communication(s) relate to? | What are the key messages? | Who are the desired audience? | What format will the communication(s) take? Where will they be shared? | When will the communication(s) be circulated/shared? | Comments
Awareness of equity and equality analysis and action plan | What is the quality and equality action plan? What has the LMNS done so far to address health inequalities? What is the action plan? How has the action plan been co-produced with women and families? | ICB, acute and primary care providers, women and families, local communities | Email newsletters, social media posts, posters, leaflets | 2022-09-01 | Summary sheet to be prepared and circulated via suggested formats
Easy read analysis document | What has N&W got in place already? Where are our areas of need? What are our areas of deprivation? Where are our VCSE's? | ICB, acute and primary care providers, women and families, local communities | ICS website, social media posts | 2022-09-01
N&W Maternity Services Co-Production Timeline | When are the listening events being held? What are the listening events? Where will they be held? | ICB, acute and primary care providers, women and families, local communities, VCSE's | Email newsletters, social media posts, posters, leaflets | 2022-10-01
Equity and Equality Action Plan Service User facing Padlet | Background to E&E Strategy, 5 Priorities, Easy read analysis, link to E&E Action Plan and Evidence | ICB, acute and primary care providers, women and families, local communities, VCSE's | Padlet webpage, social media, trust web pages, Just one Norfolk, in clinical areas on posters | 2022-09-01 | Padlet
Maternity Equity and Equality ICB web page publication | Background to E&E Strategy, 5 Priorities, Easy read analysis, links to E&E Action Plan and Evidence | ICB, acute and primary care providers, women and families, local communities, VCSE's, Stakeholders, staff | Webpage to publish Action Plan and all documents pertaining to this. | 2022-09-01 | Maternity Equity and Equality Webpage

## Measurement Plan
,
Measurement Plan
Priority | Measure | Type of Measure | Data Collection | Existing Source or New Data Collection? | Targert | Value | Comments
Priority 2: Mitigate against digital exclusion | What is the success measure? | Is this an outcome or process measure? | How will data be collected to demonstrate this measure? | Is a new data collection process required? | Target value (%) | Norfolk and Waveney value | Comments
| The number of women which have a PCSP which covers Antanatal care by 17 weeks gestation | Process | All indicators are available with breakdowns by ethnicity and index of multiple deprivation (source: MSDS) | Existing source | 90% | 90% | As per CNST : April 2022 score card: Criteria_5 PCSP - July 2022 data contained antenatal personalised care plan fields completed for 95% of women booked in the month. (MSD101/2). QEH have a digital PCSP in place NNUH & QEH are working towards implementation by end of 22/23. Both trusts currenlty have paper PCSP in place
| The number of women which have a PCSP which covers Intrapartum care by 35 weeks gestation | Process |  | Existing source | 90% | 90%
| The number of women which have a PCSP which covers Postnatal care by 37 weeks gestation | Process |  | Existing source | 90% | 90%
| The numbers of women who had all 3 in place by gestational date | Process |  | Existing source | 90% | 90% | April scorecard = QEH : 96.7 % (145/150) / N & N 96.7% (440 / 455) / JPH 54.3% (95/175) JPH following guidance form N&N to improve data recording for MSDS
Priority 3: Ensure datasets are complete and timely | Safety action 2 category 9: Data submitted to MSDS contains valid postcode for mother at booking | Process | MIS | Existing Source | 100% | 100% | April 22 Data National Dashboard AOD data collected : JPH 99% / NNUH 100% / QEH 100%
| Ethnicity data quality (source: Regional Measures Report). | Process | MIS | Existing Source | N/A | N/A | April 2022 MSDS Ethnicity : JPH 77.1 % (135/175) / NNUH 96.7% (440/455) / QEH 96.7% (145/150)
| Safety action 2, category 10: data submitted to MSDS includes a valid ethnic category for at least 80% of the women booked in the month. Not stated, missing and not known are not valid records. | Process | MIS | Exisiting Source | 100% | 100%
4b Action on maternal mortality, morbidity and experience | The Maternal Medicine Network is implementing the KPIs in the nonmandatory national service specification. They are broken down by level of deprivation of the mother’s postcode and ethnicity | Process | Maternal Medicine Network | Exisitng source | 100% | 100%
| Booking at <70 days gestation (source: Regional Measures Report) | Process | MIS | Exisiting source | N/A | N/A
| For each complex social factor grouping the number of women who attend for booking by 10, 12+6 and 20 weeks and attend the recommended number of appointments | Process | Digital Midwife | New source | N/A | N/A
| Proportion of women with complex social factors who attend booking by 10 weeks, 12+6 weeks and 20 weeks (source: Regional Measures Report) | Process | Digital Midwife | New source | N/A | N/A
| % of parent members of the MVP who are from ethnic minority groups | Process | Not collected at present | New source | N/A | N/A
| % of women attending the booking appointment who are from ethnic minority groups (source: Regional Measures Report) | Process | MIS | Exisiting source | N/A | N/A
| Ethnicity data quality (source: Regional Measures Report) | Process | MIS | Exisiting source | N/A | N/A
Priority 4c: Action on perinatal mortality and morbidity | Placement on a continuity of carer pathway – Black/Asian women | Process | MIS | New source | 75% of Black/Asian women | 75% of Black/Asian women
| Placement on a continuity of carer pathway – women living in the most deprived areas | Process | MIS | Exisiting source | 75% | 75%
| Baby Friendly accreditation | Process | Infant feeding leads | New source | 100% of trusts | 100% of trusts
| Breast milk at first feed | Outcome | MIS | Exisiting Source | 75% | 75%
| Low birth weight (<2,500g for term births) | Outcome | MIS | Exisiting Source | N/A | N/A
| Deliveries under 27 weeks | Outcome | MIS | Exisitng source | N/A | N/A
| Deliveries under 37 weeks | Outcome | MIS | Exisiting Source | N/A | N/A
Priority 4d: Support for maternity and neonatal staff | % of maternity and neonatal staff who attended training about cultural competence in the last two years | Process | Practice development midwives data sets | New source | 80% | 80%
| % of maternity and neonatal Serious Incidents relating to patient care with a valid ethnic code | Process | Safety and Quality Workstream | New source | 100% | 100%
| % of Perinatal Mortality Review Tool cases with a valid ethnic code | Process | PMRT | Exisiting Source | 100% | 100%
| WRES indicators 1 to 8 for midwives and nurses in maternity and neonatal services | Outcome | System WRES data set | Exisiting Source | N/A | N/A

## Sustainability
Sustainability and Embedding Plan
Action | Current State | Resources Needed | Who needs to be involved to achieve sustainability? | How will you know it is embedded? | Timescales and Evaluation
Which action does this relate to? | What is the current state of the action, how has it improved things? | What resources are needed to embed this action into 'business as usual'? | Who needs to be involved to embed this action and make it sustainable? | How will you know that this action is embedded and is 'business as usual'? | What are the timescales for embedding this action? How will it be evaluated?
All patient information to be culturally competent and translated into multiple languages. | Patient information has passed cultural competency assessment following development with service users, and is available in 80 languages as it is hosted on Just one Norfolk | on-going relatinship with JON. | Trust equality leads, trust communications teams, service user engagement groups. Close working relationships with JON. MVP are involved in all designs | All patient information reviewed by service users on a regular basis | 12 months, annual audit of patient information
All plans are hosted within the LMNS workstreams and are a part of the Progrmme manager sblueprint. | E&E is a default agenda item on all workstreasm and goldren thread that runs through every workstream and project, | Ongoing LMNS funding. Budget aligned to incorporate this work | on-going workstream with allocated Chairs and co-chairs with Provider Trust engagement . | when workstreams are secured with named Chairs and provider engagement | Jan 2023.
MVP funding and work plans need to reflect the new National guidence which has yet to be published. | The ICB give limited funding to the MVP. Waiting for natioal guidelines. | Increased financial resource which is alighend to national guidence, which will allow MVP increased capacity and development. | ICB and Regional teams with Natiional team. | Updated funding plan with the MVP will be agreed and MOU will reflect increased finalacial offer and workplan. | Unknown. Regiona are awaiiting guidence
Sustainability of the LMNS team for staff | The Lead midwife and Better Birth midwives are now substantive posts | Secured funding stream required to allow for secure contracts and post for the remaining staff | ICB and Region, | The remining Team contracts are made substantive. | Team contracts in place.
Sustainablity of LMNS monies. | Funding comes to the LMNS on an annual basis which makes plans for deliverabe outcomes for the next 5 years complex. | A funding plan to the LMNS/ICB which give assurance of future funding to allow the ICB and LMNS to make secure financial decsiions based on allocated funding streams | ICB/LMNS finance and Regional finance teams | financial plan in place. | Needs to be reviewed.
Maternity trust buy in to plan to ensure it is delivered | Plan to be circulated at LMNS board for comments August 17th and then approval September 28th prior to submission. | None | Workstreams attended by LMNS trust (as per current practice). | Workstream attendance and completion of actions | 2024-03-01
co-production | Current VCSE collaboration in development stages whis will inform further co-production opportunities alongside the MVP. Trusts will be included in this as they may be able to identify resources to work with VCSE organisations within their demographic. | Ongoing realtionships with Community Action Norfolk, Norfolk Community Foundation. Secured funding for MVP and renewal of the MOU which is scheduled to happen in October 2022. Funding has been identified within the LMNS budget to support the current round of VCSE engagement events - further funding will need to be identified for future events. | JoN, VCSE, Public Health, Primary Care, Norfolk County Council, MVP, Trusts | MVP embedded with MOU and ongoing contracts. Professional Partners embedded through attendance at LMNS Board. Embedding of VCSE sector will be monitored through continued engagement as the project progresses, however we currently have established an ongoing relationship with Community Action Norfolk and Norfolk Community Foundation who work as equal partners with us the VCSE will continue to grow as relationships develop | See VCSE timetable, first round of this work will complete by Nov 2023